## Sprint 2 Plan
SPRINT 2: AUTHORING LIFECYCLE + SOCIAL INTERACTIONS
12 items ¦ ~1 week ¦ Drop edit/delete, drafts, mentions, role toggle, sessions
Sprint 2A: Authoring Lifecycle — 5 items
# | Row ID | Capability | What Exists | Effort | Implementation | Dependencies
1 | AUTH-001 | Drop drafts (durable object) | DropDraft type + validateDraft() in authoring-pipeline.ts | L | Add drafts[] to BffDatabase, BFF saveDraft/listDrafts/deleteDraft methods, workshop drafts list page, auto-save in create stepper | None — standalone
2 | AUTH-003 | Drop edit after publish | createDropVersion() + DropVersion type already in BFF | M | Add editDrop() BFF method that mutates drop fields + creates a version snapshot, edit form reusing stepper components, API route | None
3 | AUTH-004 | Drop delete with cascade | executeAccountDeletion cascade is the pattern | M | Add deleteDrop() BFF method: remove from catalog, cascade comments/likes/saves/ownerships/versions, API route, workshop UI button | None
4 | AUTH-005 | Scheduled release | WorldReleaseQueue + DropDraftStatus has 'scheduled' | M | Add scheduledAt to Drop, BFF scheduleDropRelease() method, visibility='scheduled' until release time, cron-compatible check | None
5 | AID-012 | Role toggle (collector ↔ creator) | Roles array on session, setupCreatorStudio exists | M | Add toggleActiveRole() to session, nav role indicator, settings toggle, creator-only routes check active role not just roles[] | None
Sprint 2B: Social Interactions — 3 items
# | Row ID | Capability | What Exists | Effort | Implementation | Dependencies
6 | SOC-011 | Tag/mention in post or comment | MentionContext type + isMentionAllowed() helper + comment_mention notification type | M | Add @mention parser to comment/post body, resolve handles, emit mention notifications, autocomplete UI component | None
7 | AID-015 + AID-016 | Session management + revoke | SessionRecord in BffDatabase, sessions table | M | Add listActiveSessions() + revokeSession() to BFF, new settings page, device/IP display (from session metadata) | None
8 | AID-002 | OAuth sign-in (Google, Apple) | SocialAuthButtons component + signInWithOAuth() call | M | Configure OAuth providers in Supabase dashboard, add callback route, test provider-specific flows, update sign-up/sign-in pages | Supabase config
Sprint 2C: Quick Polish — 4 items (fast, can parallelize)
# | Row ID | Capability | What Exists | Effort | Implementation | Dependencies
9 | PRV-003/SOC-024 | Private studio + follower approval | Sprint 1 wired isPrivate, follower requests, approval flow | S | DONE in Sprint 1 — BFF + API + settings UI all exist. Mark complete. | Sprint 1 ✓
10 | AID-038 | Verification status badge in workshop | VerificationBadge type exists in domain | S | Display badge component in workshop header if account is verified (read-only — actual verification is AID-037 Wave 6) | None
11 | PRV-012 | Appeal a content takedown | Appeal flow exists for comments (appealRequestedAt) | S | Extend appeal to TownhallPost moderation (appealTownhallPost already exists). Wire appeal button in UI for moderated posts. | None
12 | AUTH-022 | Multi-image posts (schema only) | TownhallPost has single text body | M | Add mediaUrls[] to TownhallPost type, update createPost to accept multiple media, carousel renderer placeholder | None

## Deferred (Sprint 3+)
DEFERRED TO SPRINT 3+ — Not launch-blocking
These require significant new infrastructure or are growth-phase features
Row ID | Capability | Why Deferred | Target Sprint | Effort | Blocker
AID-017 | Verification badge workflow | Requires ops moderation queue — growth feature, not launch | 3 | L | Ops tooling
AID-018 | Anti-impersonation review queue | Paired with AID-017 — same ops queue | 3 | L | Ops tooling
AID-026 | Multiple accounts | Complex session isolation — growth feature | 4 | L | Auth architecture
AID-037 | Identity verification doc upload | Requires secure document handling + ops review | 3 | L | Compliance
AUTH-021 | Polls / Q&A post types | New interactive schema — growth feature | 3 | L | Post type system
CONS-018 | External embed (oEmbed) | Provenance iframe needs security review | 3 | M | Security review
SOC-012 | Repost / quote-post | New post type variant — growth feature | 3 | M | Post type system
MSG-009 | Voice messages in DMs | Audio recording + playback — growth feature | 4 | L | Media pipeline
MSG-010 | Image/file attachments in DMs | File upload in messages — growth feature | 3 | M | Media pipeline
PIPE-001 | Video transcoding | Infrastructure — Supabase Edge or external | Ops | L | Pipeline setup
PIPE-002 | Adaptive bitrate streaming | Paired with PIPE-001 | Ops | L | Pipeline setup
PIPE-003 | Audio transcoding | Same pipeline as PIPE-001 | Ops | M | Pipeline setup
PIPE-013 | CDN configuration | Ops-level config, not app code | Ops | M | Infrastructure
PRF-007 | Rate limiting | Middleware — deploy-time concern | Ops | M | Infrastructure
SEC-010 | Audit logging | Structured logger — ops concern | Ops | M | Infrastructure
SEC-020 | Encryption at rest | Supabase handles — verify + document | Ops | S | Infrastructure