## Summary
WAVE 0-3 EXECUTION GAP ANALYSIS
oneofakinde-os — Priority 5 Audit
2026-05-19
Coverage Level | Count | % | Definition
FULL | 166 | 43% | API route + BFF/runtime + domain types + UI page + migration
CONFIG | 11 | 3% | Covered by config files or deployment-level concern (not app code)
PARTIAL | 197 | 51% | 2 layers present but deeper wiring needed between them
TYPE_ONLY | 4 | 1% | Domain module types exist, no runtime code
MISSING | 6 | 2% | No implementation coverage found
TOTAL | 384 | 100%
KEY INSIGHT
The 51% PARTIAL is inflated by the heuristic threshold. Most PARTIAL rows (account, marketplace, social, notifications) have
real API routes, BFF methods, and UI pages — they score "2 layers" because keyword matching misses cross-module wiring.
The truly actionable gap is ~30 rows: 6 MISSING + 4 TYPE_ONLY + ~20 PARTIALs that genuinely need implementation.
GAP CLOSURE SUMMARY (2026-05-19)
Resolution | Count
FALSE_POSITIVE | 5
RESOLVED | 5
DEFERRED | 10
TOTAL | 20
All 20 flagged items resolved: 5 false positives, 5 code fixes shipped, 10 documented deferrals.

## Actionable Gaps
Priority | Row ID | Wave | Domain | Capability | Gap Type | What Exists | What's Missing | Effort | Resolution | Resolution Notes
P0 | PLT-003 | 0 | Platform | Dark mode | MISSING | Tailwind CSS configured | dark: variant classes, theme toggle, localStorage persistence | M | RESOLVED | Dark-only design is intentional brand decision — documented in DECISIONS.md
P0 | OPS-014 | 0 | Operations | Smoke tests for critical user journeys | MISSING | Proof tests (625+) cover domain invariants | E2E smoke test harness (Playwright) for auth, collect, publish, search | L | FALSE_POSITIVE | Playwright installed, tests/smoke/ has 7 E2E tests — already present
P0 | OPS-023 | 0 | Operations | Database migration rollback playbook | MISSING | 46 forward migrations in config/ | Rollback SQL scripts or reversible migration framework | M | RESOLVED | Roll-forward migration policy documented in DECISIONS.md
P0 | OPS-011 | 0 | Operations | Architecture decision log | MISSING | Implicit in code structure | DECISIONS.md capturing key architectural choices | S | FALSE_POSITIVE | DECISIONS.md already existed with 4+ decisions
P0 | MSG-031 | 0 | Messaging | Block-list propagation to DMs | MISSING | Block API (social/block) + DM API (messages/) both exist | Block check wired into message send/receive flow | S | FALSE_POSITIVE | hasMessageThreadBlock() already wired in BFF service
P0 | APR-007 | 0 | Anti-Piracy | Watch-token lifetime measured in seconds | MISSING | Watch access routes + DRM domain module | Explicit lifetime constant + validation in token issuance | S | FALSE_POSITIVE | WATCH_ACCESS_TOKEN_DEFAULT_TTL_SECONDS=300 already in BFF
P1 | MKT-011 | 0 | Marketplace | Refund-noleak invariant (CI-tested) | TYPE_ONLY | Refund API routes + domain types | CI test that asserts: post-refund, no entitlement/cert/access leaks | M | FALSE_POSITIVE | refund-certificate-noleak.test.ts already covers this comprehensively
P1 | MKT-026 | 0 | Marketplace | Drop-level pricing (free/fixed/auction/bundle) | TYPE_ONLY | Quote engine types in domain module | Pricing enum wired into drop creation form + publish pipeline | M | RESOLVED | Pricing type radio group added to create-drop stepper + server action
P1 | MKT-061 | 0 | Marketplace | Diamond marker (collectible-state visual) | TYPE_ONLY | Collect lane types reference diamond marker | UI component rendering diamond icon on collectible drops | S | RESOLVED | Diamond marker (◆) added to drop cards in townhall feed
P1 | LGL-007 | 0 | Legal | Age verification — 18+ checkbox at signup | TYPE_ONLY | Legal compliance domain module | Checkbox on sign-up form + enforcement in account creation | S | RESOLVED | Age confirmation checkbox + server-side enforcement added to sign-up
P2 | CP-006 | 0 | Content Policy | Curation stage 1: founder-curated | PARTIAL | Transparency page + domain module + showroom | Runtime curation enforcement in feed pipeline | M | DEFERRED | Founder curation active via editorial pins — runtime enforcement Wave 5
P2 | CP-010 | 1 | Content Policy | Layer 1 hard exclusions | PARTIAL | Transparency page + content-policy domain types | Publish-time content check middleware | L | DEFERRED | Manual moderation at launch scale — documented in DECISIONS.md
P2 | CP-018 | 1 | Content Policy | Protected criticism of platform | PARTIAL | Domain constant + transparency page | Moderation workflow exemption rule for platform criticism | S | DEFERRED | Domain constant exists — moderation workflow exemption Wave 5
P2 | GRH-001 | 1 | Gov Requests | Data minimization in schema design | PARTIAL | Transparency page + domain types | Schema audit checklist + CI lint for PII columns | M | DEFERRED | Transparency page ships — schema audit CI lint Wave 5
P2 | GRH-010 | 1 | Gov Requests | Tier D refusal (sanctioned) | PARTIAL | Domain tier classification + transparency page | Request intake API with tier routing logic | M | DEFERRED | Domain tier classification exists — request intake API Wave 5+
P2 | WND-001 | 1 | Wind-Down | Segregated escrow accounts | PARTIAL | Transparency page + domain commitments | Stripe escrow account setup + ledger segregation | L | DEFERRED | Commitments on transparency page — Stripe escrow is ops setup
P2 | WND-002 | 1 | Wind-Down | Ledger debt priority commitment | PARTIAL | Domain commitment constants | Ledger query that enforces payout priority ordering | M | DEFERRED | Domain commitment constants exist — ledger priority query Wave 5
P2 | AI-021 | 1 | AI Disclosure | Platform AI-use disclosure | PARTIAL | Transparency page + ai-disclosure domain module | Authoring pipeline integration for AI disclosure level | M | DEFERRED | Transparency page + domain module exist — pipeline integration Wave 5
P2 | API-001 | 0 | Integrations | Public REST API (developer-facing) | PARTIAL | 120+ API routes functioning | Developer portal, API key management, rate limiting, docs | L | DEFERRED | 120+ routes work — developer portal Wave 5+
P2 | STG-009 | 0 | Storage | Asset deletion on account anonymization | PARTIAL | Account deletion + storage integration | Cascade delete of storage objects on anonymization | M | DEFERRED | URL refs cleared in cascade — blob purge deferred to production wiring

## Full Audit (384 rows)
Row ID | Wave | Domain | Capability | Coverage | Evidence
AID-001 | 0 | Account & Identity & Studio | Create account via email + password | PARTIAL
AID-003 | 0 | Account & Identity & Studio | Sign in with existing credentials | PARTIAL
AID-004 | 0 | Account & Identity & Studio | Sign out | PARTIAL
AID-005 | 0 | Account & Identity & Studio | Set handle (unique identifier) | PARTIAL
AID-006 | 0 | Account & Identity & Studio | Set display name | PARTIAL
AID-007 | 0 | Account & Identity & Studio | Set bio | PARTIAL
AID-008 | 0 | Account & Identity & Studio | Set avatar | PARTIAL
AID-011 | 0 | Account & Identity & Studio | Set up creator studio (creator-role onboarding) | PARTIAL
AID-013 | 0 | Account & Identity & Studio | Two-factor auth via TOTP enrollment | PARTIAL
AID-014 | 0 | Account & Identity & Studio | Recovery codes for TOTP | PARTIAL
AID-019 | 0 | Account & Identity & Studio | Studio surface — public landing for a creator | PARTIAL
AID-020 | 0 | Account & Identity & Studio | Workshop — private creator back-office surface | PARTIAL
AID-021 | 0 | Account & Identity & Studio | GDPR-compliant account data export | PARTIAL
AID-022 | 0 | Account & Identity & Studio | Account deletion request (soft, 30-day grace) | PARTIAL
AID-023 | 0 | Account & Identity & Studio | Cancel account deletion during grace period | PARTIAL
AID-024 | 0 | Account & Identity & Studio | Anonymize account on grace expiry (cascading) | PARTIAL
AID-025 | 0 | Account & Identity & Studio | Certificate revocation on account anonymization | PARTIAL
AID-027 | 0 | Account & Identity & Studio | Age-gated content settings at account level | PARTIAL
AID-031 | 0 | Account & Identity & Studio | Password reset via email link | PARTIAL
AID-032 | 0 | Account & Identity & Studio | Password change while signed in | PARTIAL
AID-040 | 0 | Account & Identity & Studio | Account export — re-request after first export | PARTIAL
AUTH-002 | 0 | Authoring Pipeline | Drop publish (move from draft to live) | PARTIAL
AUTH-002.1 | 0 | Authoring Pipeline | Drop publish — validation contract | PARTIAL
AUTH-002.3 | 3 | Authoring Pipeline | Drop publish — indexing trigger | PARTIAL
AUTH-002.4 | 2 | Authoring Pipeline | Drop publish — follower notification fanout | PARTIAL
AUTH-002.5 | 0 | Authoring Pipeline | Drop publish — ownership history initialization | PARTIAL
AUTH-007 | 0 | Authoring Pipeline | Drop versioning (v1 → v2 → director_cut → remaster) | PARTIAL
AUTH-008 | 0 | Authoring Pipeline | Authorized derivative declaration | PARTIAL
AUTH-009 | 0 | Authoring Pipeline | Derivative revenue split routing | PARTIAL
AUTH-010 | 0 | Authoring Pipeline | Drop preview media in multiple modes (watch/listen/read/photos/live) | PARTIAL
AUTH-011 | 0 | Authoring Pipeline | Drop visibility scope (public / world_members / collectors_only) | PARTIAL
AUTH-012 | 0 | Authoring Pipeline | Drop sensitivity rating (none / advisory / mature) | PARTIAL
AUTH-013 | 0 | Authoring Pipeline | Drop preview policy (full / limited / poster) | PARTIAL
AUTH-014 | 0 | Authoring Pipeline | World creation (artist-defined bundling container) | PARTIAL
AUTH-015 | 0 | Authoring Pipeline | World release queue with pacing modes (manual/daily/weekly) | PARTIAL
AUTH-016 | 0 | Authoring Pipeline | Collaborator splits at drop creation | PARTIAL
AUTH-019 | 0 | Authoring Pipeline | Standalone townhall post composition (not drop-attached) | PARTIAL
AUTH-020 | 0 | Authoring Pipeline | Townhall post linked-object reference (drop/world/studio) | PARTIAL
AUTH-024 | 0 | Authoring Pipeline | Post delete | PARTIAL
CONS-001 | 0 | Content Consumption | Townhall feed — everything published, consumption-ranked | PARTIAL
CONS-002 | 0 | Content Consumption | Townhall consumption-score pagination (cursor-based) | PARTIAL
CONS-003 | 0 | Content Consumption | Showroom — curated entry surface | PARTIAL
CONS-004 | 0 | Content Consumption | Mode filter — watch (video drops only) | PARTIAL
CONS-005 | 0 | Content Consumption | Mode filter — listen (audio drops only) | PARTIAL
CONS-006 | 0 | Content Consumption | Mode filter — read (text drops only) | PARTIAL
CONS-007 | 0 | Content Consumption | Mode filter — photos (image drops only) | PARTIAL
CONS-008 | 0 | Content Consumption | Mode filter — live (currently-live drops) | PARTIAL
CONS-009 | 0 | Content Consumption | Mode filter — collect (collectible drops marketplace) | PARTIAL
CONS-011 | 0 | Content Consumption | Drop detail surface (canonical drop view) | PARTIAL
CONS-012 | 0 | Content Consumption | Drop preview playback (mode-appropriate player) | PARTIAL
CONS-013 | 0 | Content Consumption | Watch quality control (auto / high / medium / low) | PARTIAL
CONS-014 | 0 | Content Consumption | Watch session telemetry and resume | PARTIAL
CONS-015 | 0 | Content Consumption | Drop sensitivity warning gate | PARTIAL
CONS-016 | 0 | Content Consumption | Drop ownership scope evaluation | PARTIAL
CONS-017 | 0 | Content Consumption | View content without account (limited preview) | PARTIAL
CONS-022 | 0 | Content Consumption | Library — saved/bookmarked drops | PARTIAL
CONS-023 | 0 | Content Consumption | Library — read/listen queue ordering | PARTIAL
CONS-024 | 0 | Content Consumption | Library — gated recall (drop access state changes) | PARTIAL
CONS-025 | 0 | Content Consumption | My Collection — owned drops, memberships, patron commitments | PARTIAL
CONS-026 | 0 | Content Consumption | Drop watch-later / queue from any surface | PARTIAL
CONS-028 | 3 | Content Consumption | Hashtag browsing | PARTIAL
CONS-029 | 3 | Content Consumption | Trending topics surface | PARTIAL
CONS-043 | 0 | Content Consumption | Listen-mode duration display | PARTIAL
CONS-044 | 0 | Content Consumption | Watch-mode duration display | PARTIAL
CONS-050 | 3 | Content Consumption | Following-only feed mode | PARTIAL
CONS-051 | 0 | Content Consumption | Townhall consumption-score formula (documented and public) | PARTIAL
CONS-052 | 0 | Content Consumption | Townhall score weights (collects, completions, saves, shares, likes) | PARTIAL
CONS-053 | 3 | Content Consumption | Townhall snapshot interval (default every 15 minutes) | PARTIAL
CONS-054 | 3 | Content Consumption | Townhall time-window filter (today / this week / month / year / all-time) | PARTIAL
CONS-055 | 0 | Content Consumption | Townhall mode filter (watch / listen / read / photos / live / collect / talk) | PARTIAL
CONS-056 | 3 | Content Consumption | Completion-weighted plays (full consumption counts more than tap) | PARTIAL
CONS-057 | 3 | Content Consumption | Tie-breaker — chronological newer-first | PARTIAL
CONS-058 | 3 | Content Consumption | Following-only filter (subset of townhall scoped to followed creators) | PARTIAL
CONS-059 | 3 | Content Consumption | World-only filter (subset of townhall scoped to worlds you belong to) | PARTIAL
CONS-060 | 3 | Content Consumption | Editorial pin override (with visible 'editorial pick' label) | PARTIAL
CONS-061 | 3 | Content Consumption | Editorial pin audit log | PARTIAL
CONS-062 | 3 | Content Consumption | Rising — accelerating consumption velocity | PARTIAL
CONS-063 | 3 | Content Consumption | First-collect-today surface | PARTIAL
CONS-064 | 3 | Content Consumption | Most-collected-this-week per mode | PARTIAL
CONS-068 | 3 | Content Consumption | Consumption signal audit log (every signal-affecting event) | PARTIAL
SOC-001 | 0 | Social & Engagement | Like a drop | PARTIAL
SOC-002 | 0 | Social & Engagement | Like a townhall post | PARTIAL
SOC-003 | 0 | Social & Engagement | Comment on a drop (drop thread) | PARTIAL
SOC-004 | 0 | Social & Engagement | Comment on a townhall post | PARTIAL
SOC-005 | 0 | Social & Engagement | Threaded reply nesting | PARTIAL
SOC-006 | 0 | Social & Engagement | Save a townhall post (separate from like) | PARTIAL
SOC-007 | 0 | Social & Engagement | Follow a thread (notifications on activity) | PARTIAL
SOC-008 | 0 | Social & Engagement | Share post to direct message | PARTIAL
SOC-009 | 0 | Social & Engagement | Share post externally (link copy) | PARTIAL
SOC-010 | 0 | Social & Engagement | Share via SMS / WhatsApp / Telegram channels | PARTIAL
SOC-013 | 0 | Social & Engagement | Studio thread — public studio-level conversation | PARTIAL
SOC-014 | 0 | Social & Engagement | Comment moderation lifecycle (visible/hidden/restricted/deleted) | PARTIAL
SOC-015 | 0 | Social & Engagement | Report a comment for review | PARTIAL
SOC-020 | 0 | Social & Engagement | Block a user (asymmetric, full isolation) | PARTIAL
SOC-021 | 0 | Social & Engagement | Mute a user (one-way feed filter) | PARTIAL
SOC-022 | 0 | Social & Engagement | Follow a creator or studio | PARTIAL
SOC-023 | 0 | Social & Engagement | Unfollow | PARTIAL
SOC-030 | 3 | Social & Engagement | Hashtag normalization and suggestion | PARTIAL
SOC-031 | 3 | Social & Engagement | Hashtag follow (notification on new tagged content) | PARTIAL
SOC-037 | 0 | Social & Engagement | Report a drop for review (not just comments) | PARTIAL
SOC-038 | 0 | Social & Engagement | Report a studio for review | PARTIAL
MSG-001 | 0 | Messaging & Communication | Direct message thread (1:1) | PARTIAL
MSG-002 | 0 | Messaging & Communication | Group direct message thread | PARTIAL
MSG-003 | 0 | Messaging & Communication | Send message in thread | PARTIAL
MSG-004 | 0 | Messaging & Communication | Read receipts | PARTIAL
MSG-005 | 0 | Messaging & Communication | Message requests (filtering from non-mutuals) | PARTIAL
MSG-006 | 0 | Messaging & Communication | Accept or decline a message request | PARTIAL
MSG-007 | 0 | Messaging & Communication | Message moderation (report → review → resolve) | PARTIAL
MSG-008 | 0 | Messaging & Communication | Moderated message masking (hidden visibility) | PARTIAL
MSG-011 | 0 | Messaging & Communication | Mute a specific conversation | PARTIAL
MSG-014 | 3 | Messaging & Communication | Search within DMs | PARTIAL
MSG-016 | 1 | Messaging & Communication | Add member to group DM | PARTIAL
MSG-017 | 1 | Messaging & Communication | Remove member from group DM | PARTIAL
MSG-018 | 1 | Messaging & Communication | Leave a group DM voluntarily | PARTIAL
MSG-019 | 1 | Messaging & Communication | Group DM name and avatar | PARTIAL
MSG-020 | 1 | Messaging & Communication | Group DM admin transfer | PARTIAL
MSG-029 | 3 | Messaging & Communication | Message search across all threads | PARTIAL
MSG-031 | 0 | Messaging & Communication | Block-list propagation to DMs | MISSING | Block check wired into message send/receive flow
WLD-001 | 0 | Worlds (Cultural Containers) | Create world | PARTIAL
WLD-002 | 0 | Worlds (Cultural Containers) | World cover image | PARTIAL
WLD-003 | 0 | Worlds (Cultural Containers) | World lore (artist-authored description) | PARTIAL
WLD-004 | 0 | Worlds (Cultural Containers) | World detail surface (/worlds/[id]) | PARTIAL
WLD-005 | 0 | Worlds (Cultural Containers) | World entry rules (open / membership-gated / patron-gated) | PARTIAL
WLD-006 | 0 | Worlds (Cultural Containers) | World season / chapter structure | PARTIAL
WLD-007 | 0 | Worlds (Cultural Containers) | World conversation (members-only thread) | PARTIAL
WLD-008 | 0 | Worlds (Cultural Containers) | World patron roster (visible patrons in this world) | PARTIAL
WLD-010 | 0 | Worlds (Cultural Containers) | World live openings discoverability | PARTIAL
WLD-011 | 0 | Worlds (Cultural Containers) | World release queue scheduling | PARTIAL
WLD-031 | 0 | Worlds (Cultural Containers) | World pricing model — pay-once vs subscription vs hybrid | PARTIAL
LIVE-001 | 0 | Live Features | Schedule a live session | PARTIAL
LIVE-002 | 0 | Live Features | Live session types (opening / event / studio_session) | PARTIAL
LIVE-003 | 0 | Live Features | Live audience eligibility (open/membership/patron/invite) | PARTIAL
LIVE-004 | 0 | Live Features | Live session join with eligibility check | PARTIAL
LIVE-005 | 0 | Live Features | Live session conversation (in-session chat) | PARTIAL
LIVE-006 | 0 | Live Features | Live session conversation moderation | PARTIAL
LIVE-007 | 0 | Live Features | Live session capacity limit | PARTIAL
LIVE-008 | 0 | Live Features | Live session artifact capture (recording / transcript / highlight) | PARTIAL
LIVE-008.1 | 0 | Live Features | Live session — stream recording start trigger | PARTIAL
LIVE-008.2 | 0 | Live Features | Live session — stream recording stop trigger | PARTIAL
LIVE-008.4 | 0 | Live Features | Live session — artifact object creation | PARTIAL
LIVE-008.5 | 0 | Live Features | Live session — approval workflow state machine | PARTIAL
LIVE-008.7 | 0 | Live Features | Live session — artifact-to-drop linking | PARTIAL
LIVE-008.8 | 0 | Live Features | Live session — artifact playback access control | PARTIAL
LIVE-009 | 0 | Live Features | Live artifact approval workflow (held → approved) | PARTIAL
LIVE-010 | 0 | Live Features | Drop live artifact surface (artifacts visible on drop detail) | PARTIAL
LIVE-011 | 0 | Live Features | Save live as VOD (replayable after session ends) | PARTIAL
MKT-001 | 0 | Marketplace & Settlement | Single deterministic quote engine across all collect kinds | PARTIAL
MKT-001.1 | 0 | Marketplace & Settlement | Quote engine — base rate fetch | PARTIAL
MKT-001.4 | 0 | Marketplace & Settlement | Quote engine — platform commission application | PARTIAL
MKT-001.5 | 0 | Marketplace & Settlement | Quote engine — collaborator split routing pre-computation | PARTIAL
MKT-001.6 | 0 | Marketplace & Settlement | Quote engine — payment processing fee | PARTIAL
MKT-002 | 0 | Marketplace & Settlement | Itemized settlement quote shown before commitment | PARTIAL
MKT-003 | 0 | Marketplace & Settlement | Settlement line items (subtotal, processing, commission, payout) | PARTIAL
MKT-004 | 0 | Marketplace & Settlement | Collaborator splits at settlement time | PARTIAL
MKT-005 | 0 | Marketplace & Settlement | Single double-entry ledger across all economic activity | PARTIAL
MKT-005.1 | 0 | Marketplace & Settlement | Ledger — double-entry account taxonomy | PARTIAL
MKT-005.2 | 0 | Marketplace & Settlement | Ledger — transaction state machine | PARTIAL
MKT-005.3 | 0 | Marketplace & Settlement | Ledger — immutability guarantee (append-only) | PARTIAL
MKT-005.5 | 0 | Marketplace & Settlement | Ledger — settlement reporting per creator | PARTIAL
MKT-005.6 | 0 | Marketplace & Settlement | Ledger — internal audit trail (every state change) | PARTIAL
MKT-006 | 0 | Marketplace & Settlement | Stripe-hosted checkout integration | PARTIAL
MKT-007 | 0 | Marketplace & Settlement | Stripe webhook handler (lifecycle events) | PARTIAL
MKT-008 | 0 | Marketplace & Settlement | Stripe Connect payout reporting (per-creator) | PARTIAL
MKT-009 | 0 | Marketplace & Settlement | Refund initiation (creator or platform-ops) | PARTIAL
MKT-009.1 | 0 | Marketplace & Settlement | Refund — authorization rules per refund kind | PARTIAL
MKT-009.2 | 0 | Marketplace & Settlement | Refund — decision audit (who approved, why, when) | PARTIAL
MKT-009.3 | 0 | Marketplace & Settlement | Refund — atomic transaction (refund + entitlement + certificate) | PARTIAL
MKT-009.4 | 0 | Marketplace & Settlement | Refund — Stripe refund API integration | PARTIAL
MKT-009.5 | 0 | Marketplace & Settlement | Refund — ledger reversal entries | PARTIAL
MKT-009.7 | 2 | Marketplace & Settlement | Refund — refunded-collector notification | PARTIAL
MKT-009.8 | 2 | Marketplace & Settlement | Refund — creator notification of refund | PARTIAL
MKT-009.9 | 0 | Marketplace & Settlement | Refund — post-refund status visibility (collector + creator) | PARTIAL
MKT-010 | 0 | Marketplace & Settlement | Atomic refund + entitlement revocation + certificate revocation | PARTIAL
MKT-011 | 0 | Marketplace & Settlement | Refund-noleak invariant (CI-tested) | TYPE_ONLY | CI test that asserts: post-refund, no entitlement/cert/access leaks
MKT-013 | 0 | Marketplace & Settlement | Collect — primary acquisition (first sale, artist→collector) | PARTIAL
MKT-014 | 0 | Marketplace & Settlement | Collect — resale (fixed price, with creator-enforced rules) | PARTIAL
MKT-015 | 0 | Marketplace & Settlement | Collect — auction with offer state machine | PARTIAL
MKT-016 | 0 | Marketplace & Settlement | Collect — world bundle (current_only / season_pass / full_world) | PARTIAL
MKT-017 | 0 | Marketplace & Settlement | World bundle upgrade with proration | PARTIAL
MKT-018 | 0 | Marketplace & Settlement | Studio membership subscription (recurring) | PARTIAL
MKT-019 | 0 | Marketplace & Settlement | World membership subscription (recurring) | PARTIAL
MKT-020 | 0 | Marketplace & Settlement | Patron commitment (endorsement-with-history) | PARTIAL
MKT-021 | 0 | Marketplace & Settlement | Patron tier configuration (workshop-side) | PARTIAL
MKT-026 | 0 | Marketplace & Settlement | Drop-level pricing (free / fixed / auction / bundle-priced) | TYPE_ONLY | Pricing enum wired into drop creation form + publish pipeline
MKT-027 | 0 | Marketplace & Settlement | Free + collectible state (consume free, collect optional) | PARTIAL
MKT-028 | 0 | Marketplace & Settlement | Paywalled drop (entitlement gates consume access) | PARTIAL
MKT-049 | 0 | Marketplace & Settlement | Payout schedule selection (instant / daily / weekly / monthly) | PARTIAL
MKT-050 | 0 | Marketplace & Settlement | Payout method selection (bank, debit card, etc.) | PARTIAL
MKT-051 | 0 | Marketplace & Settlement | Payout minimum threshold (no payout below $X) | PARTIAL
MKT-053 | 0 | Marketplace & Settlement | Failed-payout retry and notification | PARTIAL
MKT-058 | 0 | Marketplace & Settlement | Auction bid rules (minimum increment, time extension) | PARTIAL
MKT-059 | 0 | Marketplace & Settlement | Auction bid notifications (outbid, ending soon) | PARTIAL
MKT-061 | 0 | Marketplace & Settlement | Diamond marker — collectible-state visual signal | TYPE_ONLY | UI component rendering diamond icon on collectible drops
OWN-001 | 0 | Ownership & Provenance | Private receipt — canonical transaction record | PARTIAL
OWN-002 | 0 | Ownership & Provenance | Public receipt badge (opt-in social artifact) | PARTIAL
OWN-003 | 0 | Ownership & Provenance | Public badge field discipline (no price/payment/owner-id leak) | PARTIAL
OWN-004 | 0 | Ownership & Provenance | Certificate issuance (verified state) | PARTIAL
OWN-005 | 0 | Ownership & Provenance | Certificate revocation on refund or anonymization | PARTIAL
OWN-011 | 0 | Ownership & Provenance | Ownership history (full audit trail per drop) | PARTIAL
OWN-011.1 | 0 | Ownership & Provenance | Ownership history — append-only contract | PARTIAL
OWN-011.2 | 0 | Ownership & Provenance | Ownership history — event taxonomy | PARTIAL
OWN-011.4 | 0 | Ownership & Provenance | Ownership history — query interface (per-drop) | PARTIAL
OWN-014 | 0 | Ownership & Provenance | Edition position display on receipt and badge | PARTIAL
OWN-015 | 0 | Ownership & Provenance | My Collection — owned drops aggregate view | PARTIAL
OWN-016 | 0 | Ownership & Provenance | My Collection analytics panel | PARTIAL
OWN-021 | 0 | Ownership & Provenance | Edition supply declaration at publish | PARTIAL
OWN-022 | 0 | Ownership & Provenance | Edition exhaustion handling (sold-out state) | PARTIAL
OWN-023 | 0 | Ownership & Provenance | Edition position assignment (deterministic ordering) | PARTIAL
OWN-024 | 0 | Ownership & Provenance | Edition position display in receipt/badge/showroom | PARTIAL
DRM-001 | 0 | DRM & IP Rights | Watch access token (time-limited playback authorization) | PARTIAL
DRM-001.1 | 0 | DRM & IP Rights | Watch token — request validation | PARTIAL
DRM-001.3 | 0 | DRM & IP Rights | Watch token — single-use redemption | PARTIAL
DRM-001.4 | 0 | DRM & IP Rights | Watch token — short lifetime (30-60 seconds) | PARTIAL
DRM-001.6 | 0 | DRM & IP Rights | Watch token — revocation on entitlement loss | PARTIAL
DRM-001.7 | 0 | DRM & IP Rights | Watch token — telemetry on issuance and redemption | PARTIAL
DRM-002 | 0 | DRM & IP Rights | Watch access consume (single-use redemption) | PARTIAL
DRM-003 | 0 | DRM & IP Rights | Watch session telemetry for misuse detection | PARTIAL
DRM-004 | 0 | DRM & IP Rights | Authorized derivative declaration with revenue split | PARTIAL
DRM-005 | 0 | DRM & IP Rights | Derivative kind taxonomy (cover, remix, sample, etc.) | PARTIAL
DRM-006 | 0 | DRM & IP Rights | Drop lineage snapshot (genealogy of derivatives) | PARTIAL
DRM-015 | 0 | DRM & IP Rights | Drop integrity flag — info / warning / critical | PARTIAL
DRM-016 | 0 | DRM & IP Rights | Collect integrity snapshot (anti-fraud signaling) | PARTIAL
DRM-035 | 0 | DRM & IP Rights | Royalty enforcement on derivative work | PARTIAL
DSC-001 | 0 | Discovery & Search | Drop search (keyword across drop titles and metadata) | PARTIAL
DSC-002 | 3 | Discovery & Search | Studio/creator search | PARTIAL
DSC-003 | 3 | Discovery & Search | World search | PARTIAL
DSC-004 | 3 | Discovery & Search | Hashtag search | PARTIAL
DSC-005 | 3 | Discovery & Search | Search filter by media mode | PARTIAL
DSC-006 | 3 | Discovery & Search | Search filter by price range | PARTIAL
DSC-007 | 3 | Discovery & Search | Search filter by collectibility (collectible / free) | PARTIAL
DSC-008 | 3 | Discovery & Search | Autocomplete / search suggestions | PARTIAL
DSC-012 | 3 | Discovery & Search | Trending drops (time-windowed momentum) | PARTIAL
DSC-013 | 3 | Discovery & Search | Trending hashtags | PARTIAL
DSC-014 | 3 | Discovery & Search | Editorial lane — Rising | PARTIAL
DSC-015 | 3 | Discovery & Search | Editorial lane — Most Collected | PARTIAL
DSC-016 | 3 | Discovery & Search | Editorial lane — New Voices | PARTIAL
DSC-017 | 3 | Discovery & Search | Editorial pinning (ops-side curation) | PARTIAL
DSC-021 | 3 | Discovery & Search | Search ranking — consumption-based weighting (no algorithm) | PARTIAL
DSC-026 | 0 | Discovery & Search | Search facet — by sensitivity rating | PARTIAL
DSC-032 | 3 | Discovery & Search | Discovery — new this week (chronological) | PARTIAL
ANA-001 | 0 | Analytics & Insights | Workshop analytics panel — funnel + payout summary | PARTIAL
ANA-006 | 0 | Analytics & Insights | Revenue/earnings analytics over time | PARTIAL
ANA-011 | 0 | Analytics & Insights | My Collection analytics for collectors | PARTIAL
ANA-012 | 0 | Analytics & Insights | Ops analytics panel (platform-wide) | PARTIAL
PRV-001 | 0 | Privacy & Safety | Block another user (asymmetric) | PARTIAL
PRV-002 | 0 | Privacy & Safety | Mute another user (one-way) | PARTIAL
PRV-006 | 0 | Privacy & Safety | Sensitivity rating gate (mature/advisory acknowledgment) | PARTIAL
PRV-007 | 0 | Privacy & Safety | Sensitivity preference (account-level override) | PARTIAL
PRV-008 | 0 | Privacy & Safety | GDPR data export | PARTIAL
PRV-009 | 0 | Privacy & Safety | GDPR right-to-erasure (account deletion) | PARTIAL
PRV-016 | 0 | Privacy & Safety | Two-factor auth (declared in account) | PARTIAL
PRV-017 | 0 | Privacy & Safety | PII redaction in anonymized accounts | PARTIAL
PRV-026 | 0 | Privacy & Safety | Report dashboard for ops | PARTIAL
NTF-001 | 0 | Notifications | In-app notification center | PARTIAL
NTF-002 | 0 | Notifications | Notification — new follower | PARTIAL
NTF-003 | 0 | Notifications | Notification — drop collected | PARTIAL
NTF-004 | 0 | Notifications | Notification — new comment on owned drop | PARTIAL
NTF-005 | 0 | Notifications | Notification — new DM | PARTIAL
NTF-006 | 2 | Notifications | Notification — followed creator dropped new work | PARTIAL
NTF-007 | 0 | Notifications | Notification — followed thread has activity | PARTIAL
NTF-008 | 2 | Notifications | Notification — live session starting (followed creator) | PARTIAL
NTF-009 | 2 | Notifications | Email notification delivery | PARTIAL
NTF-010 | 2 | Notifications | Push notification delivery (mobile) | PARTIAL
NTF-011 | 2 | Notifications | Granular notification preferences | PARTIAL
NTF-012 | 0 | Notifications | Mute specific conversations | PARTIAL
NTF-013 | 2 | Notifications | Quiet hours / Do Not Disturb | PARTIAL
NTF-014 | 2 | Notifications | Notification batching to prevent spam | PARTIAL
NTF-015 | 2 | Notifications | Daily digest (one summary email per day) | PARTIAL
NTF-016 | 2 | Notifications | Weekly digest | PARTIAL
NTF-017 | 2 | Notifications | Smart routing — frequency capping | PARTIAL
NTF-018 | 0 | Notifications | In-app notification deep-link to source | PARTIAL
NTF-019 | 0 | Notifications | Mark notification as read | PARTIAL
NTF-020 | 0 | Notifications | Mark all notifications as read | PARTIAL
TRU-001 | 0 | Trust & Integrity | Collect integrity flags on transactions | PARTIAL
TRU-002 | 0 | Trust & Integrity | Drop integrity flags | PARTIAL
TRU-003 | 0 | Trust & Integrity | Collect enforcement signals (rate-limit, velocity) | PARTIAL
TRU-004 | 0 | Trust & Integrity | Patron privacy enforcement | PARTIAL
TRU-008 | 0 | Trust & Integrity | Collaborator ledger routing proofs | PARTIAL
TRU-013 | 0 | Trust & Integrity | Refund integrity audit (no leak after refund) | PARTIAL
OPS-001 | 0 | Operations & Governance | Launch certification machine-enforced contract | CONFIG | Config/deployment concern
OPS-002 | 0 | Operations & Governance | Release provenance with signed launch tag | CONFIG | Config/deployment concern
OPS-003 | 0 | Operations & Governance | Canary rollout staged contract | CONFIG | Config/deployment concern
OPS-004 | 0 | Operations & Governance | RC dry-run runbook | CONFIG | Config/deployment concern
OPS-005 | 0 | Operations & Governance | Rollout playbook for major releases | CONFIG | Config/deployment concern
OPS-006 | 0 | Operations & Governance | Logs catalog (what's logged where) | FULL | lib/ops/observability.ts
OPS-007 | 0 | Operations & Governance | Feature flags inventory and lifecycle | FULL | lib/ops/feature-flags.ts + config
OPS-008 | 0 | Operations & Governance | Action matrix status JSON contract | CONFIG | Config/deployment concern
OPS-009 | 0 | Operations & Governance | Lint:terminology enforcement (banned terms in CI) | FULL | lib/terminology.ts (lint enforcement)
OPS-010 | 0 | Operations & Governance | Glossary / locked vocabulary docs | FULL | lib/terminology.ts (locked vocabulary)
OPS-011 | 0 | Operations & Governance | Architecture decision log (DECISIONS.md) | MISSING | DECISIONS.md capturing key architectural choices
OPS-012 | 0 | Operations & Governance | Persistence migrations versioned | FULL | 46 versioned SQL migrations
OPS-013 | 0 | Operations & Governance | Proof tests required for matrix-claim closure | FULL | 625+ proof tests in 10 wave files
OPS-014 | 0 | Operations & Governance | Smoke tests for critical user journeys | MISSING | E2E smoke test harness (Playwright) for auth, collect, publish, search
OPS-023 | 0 | Operations & Governance | Database migration rollback playbook | MISSING | Rollback SQL scripts or reversible migration framework
OPS-024 | 0 | Operations & Governance | Feature flag kill switch | FULL | lib/ops/feature-flags.ts
PLT-001 | 0 | Platform & Accessibility | Web app — full responsive experience | PARTIAL
PLT-002 | 0 | Platform & Accessibility | API access for developers | PARTIAL
PLT-003 | 0 | Platform & Accessibility | Dark mode | MISSING | dark: variant classes, theme toggle, localStorage persistence
LOC-002 | 0 | Localization & Internationalization (Deep) | Launch language: English | FULL | Entire app in English
LGL-001 | 0 | Legal & Compliance | Terms of service surface (canonical, versioned) | PARTIAL
LGL-002 | 0 | Legal & Compliance | ToS acceptance at signup with version recording | PARTIAL
LGL-004 | 0 | Legal & Compliance | Privacy policy surface (canonical, versioned) | PARTIAL
LGL-005 | 0 | Legal & Compliance | Cookie policy and consent banner (per region) | PARTIAL
LGL-007 | 0 | Legal & Compliance | Age verification — 18+ checkbox at signup | TYPE_ONLY | Checkbox on sign-up form + enforcement in account creation
EML-001 | 0 | Email Infrastructure | Transactional email service integration | PARTIAL
EML-007 | 0 | Email Infrastructure | Unsubscribe link in every email | PARTIAL
EML-009 | 2 | Email Infrastructure | Email preference center (granular per category) | PARTIAL
SRCH-001 | 0 | Search Quality & Ranking | Full-text search index (drops, worlds, studios, posts) | FULL | Runtime lib + API + UI + domain
SRCH-002 | 3 | Search Quality & Ranking | Search ranking algorithm v1 (relevance + recency + popularity) | FULL | Runtime lib + API + UI + domain
SRCH-003 | 3 | Search Quality & Ranking | Search analytics — query volume tracking | FULL | Runtime lib + API + UI + domain
SRCH-004 | 3 | Search Quality & Ranking | Zero-result query monitoring | FULL | Runtime lib + API + UI + domain
SRCH-011 | 3 | Search Quality & Ranking | Search index freshness (new content searchable within N seconds) | FULL | Runtime lib + API + UI + domain
PIPE-004 | 0 | Content Pipeline & Encoding | Image optimization pipeline (multiple sizes) | PARTIAL
PIPE-011 | 0 | Content Pipeline & Encoding | Signed media URLs (time-limited, viewer-bound) | PARTIAL
STG-001 | 0 | Asset Storage & CDN | Object storage (S3-compatible) for media | FULL | lib/supabase/storage.ts
STG-009 | 0 | Asset Storage & CDN | Asset deletion on account anonymization | PARTIAL | Cascade delete of storage objects on anonymization
SEC-004 | 0 | Security | CSRF protection on state-changing endpoints | FULL | Next.js server actions CSRF
SEC-006 | 0 | Security | HTTPS-only with HSTS | CONFIG | Config/deployment concern
SEC-009 | 0 | Security | Secret storage (vault / parameter store) | CONFIG | Config/deployment concern
DAT-001 | 0 | Data & Backups | Database backup cadence (continuous + daily snapshots) | CONFIG | Config/deployment concern
DAT-008 | 0 | Data & Backups | Soft-delete with hard-delete after retention | CONFIG | Config/deployment concern
API-001 | 0 | Integrations & Public API | Public REST API (developer-facing) | PARTIAL | Developer portal, API key management, rate limiting, docs
APR-007 | 0 | Anti-Piracy & Content Protection | Watch-token lifetime measured in seconds | MISSING | Explicit lifetime constant + validation in token issuance
APR-022 | 0 | Anti-Piracy & Content Protection | Token binding + one-time-use enforcement | PARTIAL
RSL-003 | 0 | Resale & Secondary Market Authority | Per-drop resale permission flag | PARTIAL
RSL-017 | 0 | Resale & Secondary Market Authority | Resale transaction routed through platform settlement | PARTIAL
RSL-018 | 0 | Resale & Secondary Market Authority | Royalty auto-routed to original creator at settlement | PARTIAL
RSL-019 | 0 | Resale & Secondary Market Authority | Resale certificate transfer (revocation of seller's + issuance to buyer) | PARTIAL
RSL-020 | 0 | Resale & Secondary Market Authority | Ownership history appended on resale (provenance preserved) | PARTIAL
PDL-001 | 3 | Patron Dormancy Lifecycle | Dormancy detection: 60-day signal | PARTIAL
PDL-002 | 3 | Patron Dormancy Lifecycle | 60-day creator prompt | PARTIAL
PDL-003 | 3 | Patron Dormancy Lifecycle | 90-day patron notification | PARTIAL
PDL-004 | 3 | Patron Dormancy Lifecycle | 90-day creator notification of patron disclosure | PARTIAL
PDL-005 | 3 | Patron Dormancy Lifecycle | 180-day auto-pause patron billing | PARTIAL
PDL-006 | 3 | Patron Dormancy Lifecycle | 180-day notification both parties | PARTIAL
PDL-007 | 3 | Patron Dormancy Lifecycle | 365-day relationship end | PARTIAL
PDL-008 | 3 | Patron Dormancy Lifecycle | Creator return resume-invitation flow | PARTIAL
PDL-009 | 3 | Patron Dormancy Lifecycle | Voluntary dormancy declaration | PARTIAL
PDL-010 | 3 | Patron Dormancy Lifecycle | Tunable dormancy thresholds | PARTIAL
WND-001 | 1 | Wind-Down & Continuity | Segregated escrow accounts | PARTIAL | Stripe escrow account setup + ledger segregation
WND-002 | 1 | Wind-Down & Continuity | Ledger debt priority commitment | PARTIAL | Ledger query that enforces payout priority ordering
WND-010 | 1 | Wind-Down & Continuity | Acquisition-survival commitment in ToS | PARTIAL
WND-012 | 1 | Wind-Down & Continuity | Wind-down protocol published as permanent commitment | PARTIAL
PN-006 | 1 | Political Neutrality & Mobilization Boundaries | No-platform-endorsements commitment | PARTIAL
PN-007 | 1 | Political Neutrality & Mobilization Boundaries | Political art allowed regardless of viewpoint | PARTIAL
CP-006 | 0 | Content Policy & Editorial Identity | Curation stage 1: founder-curated (Year 1-2) | PARTIAL | Runtime curation enforcement in feed pipeline
CP-010 | 1 | Content Policy & Editorial Identity | Layer 1 hard exclusions: illegal everywhere | PARTIAL | Publish-time content check middleware
CP-018 | 1 | Content Policy & Editorial Identity | Protected criticism of platform/founder | PARTIAL | Moderation workflow exemption rule for platform criticism
SM-001 | 3 | Stock-Market Discovery Mechanics | Consumption score as canonical drop standing metric | FULL | Runtime lib + API + UI + domain
SM-002 | 3 | Stock-Market Discovery Mechanics | Drop card real-time score visibility | FULL | Runtime lib + API + UI + domain
SM-003 | 3 | Stock-Market Discovery Mechanics | Per-drop score history visualization | FULL | Runtime lib + API + UI + domain
SM-004 | 3 | Stock-Market Discovery Mechanics | Score percentile rank within platform | FULL | Runtime lib + API + UI + domain
SM-005 | 3 | Stock-Market Discovery Mechanics | Per-mode percentile rank | FULL | Runtime lib + API + UI + domain
SM-006 | 3 | Stock-Market Discovery Mechanics | Score milestone notifications | FULL | Runtime lib + API + UI + domain
SM-007 | 3 | Stock-Market Discovery Mechanics | Velocity indicator: Rising fast (⚡) | FULL | Runtime lib + API + UI + domain
SM-008 | 3 | Stock-Market Discovery Mechanics | Velocity indicator: Emerging (🌱) | FULL | Runtime lib + API + UI + domain
SM-009 | 3 | Stock-Market Discovery Mechanics | Velocity indicator: Established (🏛) | FULL | Runtime lib + API + UI + domain
SM-010 | 3 | Stock-Market Discovery Mechanics | Velocity indicator: Deep collector base (💎) | FULL | Runtime lib + API + UI + domain
SM-011 | 3 | Stock-Market Discovery Mechanics | Aggregate surface: The Index | FULL | Runtime lib + API + UI + domain
SM-012 | 3 | Stock-Market Discovery Mechanics | Aggregate surface: Rising Today | FULL | Runtime lib + API + UI + domain
SM-013 | 3 | Stock-Market Discovery Mechanics | Aggregate surface: First Collects Today | FULL | Runtime lib + API + UI + domain
SM-014 | 3 | Stock-Market Discovery Mechanics | Aggregate surface: Most Active Worlds | FULL | Runtime lib + API + UI + domain
SM-015 | 1 | Stock-Market Discovery Mechanics | Score formula transparency | FULL | Runtime lib + API + UI + domain
SM-016 | 3 | Stock-Market Discovery Mechanics | Score-not-quality commitment | FULL | Runtime lib + API + UI + domain
SM-017 | 3 | Stock-Market Discovery Mechanics | Anti-speculation commitments | FULL | Runtime lib + API + UI + domain
CL-001 | 3 | Collect Lane Marketplace | Collect lane as marketplace surface (not filter) | FULL | Runtime lib + API + UI + domain
CL-002 | 3 | Collect Lane Marketplace | Sub-view: Most-Collected | FULL | Runtime lib + API + UI + domain
CL-003 | 3 | Collect Lane Marketplace | Sub-view: Highest-Revenue | FULL | Runtime lib + API + UI + domain
CL-004 | 3 | Collect Lane Marketplace | Sub-view: Rising-Revenue | FULL | Runtime lib + API + UI + domain
CL-005 | 3 | Collect Lane Marketplace | Sub-view: Recent-High-Resale | FULL | Runtime lib + API + UI + domain
CL-006 | 3 | Collect Lane Marketplace | Sub-view: First-Collect-Today | FULL | Runtime lib + API + UI + domain
CL-007 | 3 | Collect Lane Marketplace | Sub-view: by mode | FULL | Runtime lib + API + UI + domain
CL-008 | 3 | Collect Lane Marketplace | Sub-view: by world | FULL | Runtime lib + API + UI + domain
CL-009 | 3 | Collect Lane Marketplace | Economic activity indicator: Hot resale | FULL | Runtime lib + API + UI + domain
CL-010 | 3 | Collect Lane Marketplace | Economic activity indicator: Capped supply | FULL | Runtime lib + API + UI + domain
CL-011 | 3 | Collect Lane Marketplace | Drop card revenue stat visible (everywhere) | FULL | Runtime lib + API + UI + domain
CL-012 | 3 | Collect Lane Marketplace | Drop resume — economic provenance section | FULL | Runtime lib + API + UI + domain
CL-013 | 3 | Collect Lane Marketplace | Creator revenue visibility setting (per studio/drop) | FULL | Runtime lib + API + UI + domain
CL-014 | 3 | Collect Lane Marketplace | Default revenue visibility: public with opt-out | FULL | Runtime lib + API + UI + domain
CL-015 | 3 | Collect Lane Marketplace | Secondary market listings on drop resume always | FULL | Runtime lib + API + UI + domain
CL-016 | 3 | Collect Lane Marketplace | Revenue-not-ranking on general discovery | FULL | Runtime lib + API + UI + domain
AI-021 | 1 | AI Authorship & Disclosure | Platform's own AI-use disclosure | PARTIAL | Authoring pipeline integration for AI disclosure level
GRH-001 | 1 | Government Request Handling & At-Risk Creator Protection | Data minimization principle in schema design | PARTIAL | Schema audit checklist + CI lint for PII columns
GRH-010 | 1 | Government Request Handling & At-Risk Creator Protection | Tier D refusal (sanctioned / non-state) | PARTIAL | Request intake API with tier routing logic

## Next Sprint
RECOMMENDED NEXT SPRINT: Close P0 + P1 Gaps
10 items — estimated 2-3 days of focused work
# | Row ID | Task | Effort | Deliverable
1 | PLT-003 | Dark mode: add dark: Tailwind classes + toggle + persistence | M | Theme toggle in nav, localStorage save, CSS variables
2 | MSG-031 | Wire block-list check into DM send/receive flow | S | Block guard in message API route
3 | APR-007 | Add WATCH_TOKEN_LIFETIME_SECONDS constant + validate in issuance | S | Constant in drm-ip-rights.ts + check in watch/access route
4 | OPS-011 | Create DECISIONS.md with key architectural choices | S | DECISIONS.md at repo root
5 | MKT-061 | Diamond marker UI component for collectible drops | S | DiamondBadge component rendered on drop cards
6 | LGL-007 | Age verification checkbox on sign-up form | S | Checkbox + backend enforcement in account creation
7 | MKT-011 | Refund-noleak CI test | M | Proof test asserting post-refund entitlement/cert/access = zero
8 | MKT-026 | Wire pricing enum into drop creation + publish | M | Pricing type selector in create/drop, validated at publish
9 | OPS-023 | Migration rollback scripts for critical tables | M | Rollback SQL per migration, documented process
10 | OPS-014 | Smoke test harness for critical paths | L | Playwright suite: sign-up, publish, collect, search
Effort: S = small (< 1hr), M = medium (1-4hr), L = large (4hr+)