## Triage
W4-5 LAUNCH GAP TRIAGE
51 items → 3 buckets → Sprint 1 recommended
Bucket | Count | Description | Effort | Sprint
QUICK WIRING | 14 | Domain types exist → wire to BFF + API + UI toggle/field | 2-3 days | 1 ★
FEATURE BUILD | 23 | New screens, flows, significant backend logic needed | 3-6 weeks | 2-4
INFRASTRUCTURE | 7 | Ops/deploy-level: pipelines, CDN, rate limiting, encryption | Ongoing | 2+
DUPLICATE | 7 | Overlaps with another item — covered when parent ships | 0 | —
RECOMMENDATION
Sprint 1: Quick Wiring (14 items, ~2-3 days). Highest ROI — each item connects existing
domain types to the UI with a BFF method + API route + settings toggle. No new screens.
Priority: creator safety controls first (protect creators at launch), then authoring, then studio identity.
Row ID | Bucket | Capability | What Exists | Effort | Work Description | Sprint
SOC-016 | QUICK WIRING | Disable comments on a specific drop | commentsDisabled in social-engagement.ts | S | Add commentsDisabled to Drop, BFF toggle method, per-drop settings UI | 1
SOC-017 | QUICK WIRING | Filter comments by keyword | keywordFilters[] in social-engagement.ts | S | Add keywordFilters to Studio, BFF CRUD, settings form, filter in comment add | 1
MSG-015 | QUICK WIRING | Restrict who can DM (followers only / no one) | dmRestriction in privacy-controls.ts + creator-safety.ts | S | Add dmRestriction to Account, settings toggle, enforce in sendMessage BFF | 1
PRV-013 | DUPLICATE | Restrict DMs to mutual followers | Same as MSG-015 dmRestriction | 0 | Covered by MSG-015 — "mutual_only" is an existing enum value | —
SOC-019 | QUICK WIRING | Restrict a user (shadow-limit interactions) | RestrictedUser type in creator-safety.ts | M | Add restrictions table, BFF methods, UI button on user profiles | 1
PRV-004 | QUICK WIRING | Online-status visibility (show or hide) | onlineStatusVisible in privacy-controls.ts | S | Add field to Account, settings toggle, respect in presence rendering | 1
AUTH-006 | QUICK WIRING | Drop pinning to studio top | No type yet — add pinnedDropId to Studio | S | Add pinnedDropId to Studio, BFF pin/unpin method, workshop UI + studio display | 1
AUTH-017 | QUICK WIRING | Alt-text for image preview assets (required) | altText in authoring-pipeline.ts draft validation | S | Add altText field to create-drop stepper, pass through to createDrop action | 1
AUTH-018 | QUICK WIRING | Captions for video and audio drops | captionTrack in authoring-pipeline.ts | S | Add caption upload field to stepper, store URL on Drop, render in player | 1
AUTH-042 | DUPLICATE | Caption upload for video and audio drops | Same as AUTH-018 | 0 | Duplicate of AUTH-018 | —
SOC-018 | QUICK WIRING | Hide like counts (per-drop or globally) | No type yet — add boolean | S | Add hideLikeCounts to Studio settings, respect in townhall feed rendering | 1
MKT-030 | QUICK WIRING | Brand / sponsored content disclosure | AI disclosure pattern exists | S | Add sponsoredContentDisclosure field to Drop, display badge on drop cards | 1
AID-009 | QUICK WIRING | Set banner image on studio | No type yet — add bannerUrl | S | Add bannerUrl to Studio, upload in settings, display on studio page | 1
AID-010 | QUICK WIRING | Add multiple external profile links | No type yet — add externalLinks[] | S | Add externalLinks array to Studio, settings form, display on studio page | 1
PRV-005 | QUICK WIRING | Hide drop from specific users | No type yet — add excludedAccountIds | M | Add per-drop exclusion list, settings UI, enforce in feed/detail queries | 1
AID-002 | FEATURE BUILD | Create account via OAuth (Google, Apple) | SocialAuthButtons + Supabase signInWithOAuth | M | Configure OAuth providers in Supabase dashboard, test callback flow | 2
AID-012 | FEATURE BUILD | Switch active role (collector ↔ creator) | Roles exist in session | M | Add role toggle in nav/settings, persist active role, gate UI surfaces | 2
AID-015 | FEATURE BUILD | View active sessions across devices | Supabase auth tracks sessions | M | New settings page listing sessions, BFF method to query Supabase auth | 2
AID-016 | FEATURE BUILD | Revoke an active session remotely | Tied to AID-015 | S | Add revoke button to session list, BFF calls Supabase signOut for session | 2
PRV-010 | DUPLICATE | Active session management | Same as AID-015 | 0 | Duplicate of AID-015 | —
PRV-011 | DUPLICATE | Login activity log | Tied to AID-015 | 0 | Subset of AID-015 session list | —
AID-017 | FEATURE BUILD | Verification badge for verified identity | No type yet | L | New verification workflow: ops marks account verified, badge renders on studio | 3
AID-018 | FEATURE BUILD | Anti-impersonation review queue | No type yet | L | New moderation queue: user reports, ops reviews, action taken | 3
PRV-014 | DUPLICATE | Anti-impersonation report | Same as AID-018 | 0 | Report form is part of AID-018 flow | —
AID-026 | FEATURE BUILD | Multiple accounts (separate identities) | Supabase auth is per-email | L | Account switcher UI, session isolation, distinct auth contexts | 4
AID-037 | FEATURE BUILD | Identity verification document upload (KYC) | No type yet | L | Secure upload flow, ops review queue, status tracking | 3
AID-038 | FEATURE BUILD | Identity verification status in workshop | Tied to AID-037 | S | Display verification status badge in workshop header | 3
AUTH-001 | FEATURE BUILD | Drop draft creation (durable object) | Create stepper is in-memory state | L | Persist drafts to DB, list drafts in workshop, resume editing | 2
AUTH-003 | FEATURE BUILD | Drop edit after publish (with edit history) | editDrop refs exist in BFF | M | Edit form, BFF updateDrop method, version history tracking | 2
AUTH-004 | FEATURE BUILD | Drop delete (with cascade) | No deleteDrop in BFF | M | BFF deleteDrop with cascade to comments/library/certs, workshop UI | 2
AUTH-005 | FEATURE BUILD | Drop scheduled release | World release queue exists | M | Add scheduledAt to Drop, cron/job to publish at time, stepper field | 2
AUTH-021 | FEATURE BUILD | Polls / Q&A / interactive post objects | TownhallPost exists with text body | L | New post types: poll/QA schema, UI components, BFF methods | 3
AUTH-022 | FEATURE BUILD | Multi-image carousel posts | Single media per post | L | Multi-media array on post, swipeable carousel component, upload flow | 3
AUTH-023 | DUPLICATE | Post edit after publish | Subset of AUTH-003 | 0 | Same edit flow applies to posts — covered by AUTH-003 pattern | —
CONS-018 | FEATURE BUILD | Embed drop externally (iframe + provenance) | No embed endpoint | M | OEmbed API endpoint, iframe-safe drop preview page, embed code UI | 3
SOC-011 | FEATURE BUILD | Tag/mention user in post or comment | No mention parsing | M | Mention parser, autocomplete UI, notification on mention | 2
SOC-012 | FEATURE BUILD | Repost a townhall post | No repost type | M | Repost post type, BFF method, feed rendering, quote variant | 3
SOC-032 | DUPLICATE | Quote-post with own commentary | Variant of SOC-012 | 0 | Quote-post is repost + body — covered by SOC-012 | —
SOC-024 | FEATURE BUILD | Approve followers (private/locked account) | No follower approval flow | L | isPrivate on Account, follow-request queue, approval UI, enforce in feed | 3
PRV-003 | FEATURE BUILD | Private/locked account | Tied to SOC-024 | L | Same implementation as SOC-024 | 3
PRV-012 | FEATURE BUILD | Appeal a content takedown | Appeal exists for comments | M | Extend appeal flow to content takedowns, new moderation surface | 3
MSG-009 | FEATURE BUILD | Voice message attachments | DM system exists | L | Audio recording UI, upload, playback component in DM thread | 4
MSG-010 | FEATURE BUILD | Image/file attachments in DMs | DM system exists | M | File upload in DM compose, media display in messages, moderation | 3
PIPE-001 | INFRASTRUCTURE | Video transcoding pipeline | Domain types for quality ladder | L | Supabase Edge Function or external service (Mux/Cloudflare Stream) | Ops
PIPE-002 | INFRASTRUCTURE | Adaptive bitrate streaming (HLS/DASH) | Bitrate ladder types exist | L | Paired with PIPE-001 — transcoding outputs HLS segments | Ops
PIPE-003 | INFRASTRUCTURE | Audio transcoding pipeline | Audio quality tiers defined | M | Same pipeline as PIPE-001 for audio codecs | Ops
PIPE-013 | INFRASTRUCTURE | CDN configuration for media delivery | Supabase storage in use | M | CDN rules, cache headers, signed URL config in Supabase/Vercel | Ops
PRF-007 | INFRASTRUCTURE | Rate limiting per endpoint with backoff | No middleware yet | M | Rate-limit middleware (Vercel KV or Upstash), per-route config | Ops
SEC-001 | INFRASTRUCTURE | Rate limiting per endpoint | Same as PRF-007 | 0 | Same implementation as PRF-007 | Ops
SEC-010 | INFRASTRUCTURE | Audit logging for sensitive operations | No audit log | M | Structured audit logger, log sensitive ops to persistent store | Ops
SEC-020 | INFRASTRUCTURE | Encryption at rest for sensitive data | Supabase handles at DB level | S | Verify Supabase encryption config, document in DECISIONS.md | Ops

## Sprint 1 — Quick Wiring
SPRINT 1: QUICK WIRING
14 items ¦ ~2-3 days ¦ Creator safety → Authoring → Studio identity
# | Row ID | Capability | Priority | Implementation | Files to Touch
1 | SOC-016 | Disable comments on a specific drop | Safety P1 | Add commentsDisabled boolean to Drop type, BFF method toggleDropComments(), enforce in addTownhallComment, workshop per-drop toggle | contracts.ts, service.ts, workshop-root-screen.tsx
2 | SOC-017 | Filter comments by keyword | Safety P1 | Add keywordFilters[] to Studio, BFF upsertKeywordFilters(), check in addTownhallComment before persisting, settings form | contracts.ts, service.ts, settings-account-form.tsx
3 | MSG-015 | Restrict who can DM | Safety P1 | Add dmRestriction to Account (type exists in privacy-controls.ts), enforce in sendMessage BFF, settings toggle | contracts.ts, service.ts, settings-account-form.tsx
4 | SOC-019 | Restrict a user (shadow-limit) | Safety P1 | Add restrictions DB collection, BFF restrictUser/unrestrictUser, enforce in feed/comment visibility, UI button | contracts.ts, service.ts, persistence.ts, studio-screen.tsx
5 | PRV-004 | Online-status visibility toggle | Safety P1 | Add onlineStatusVisible to Account (type exists), settings checkbox, respect in presence card rendering | contracts.ts, service.ts, settings-account-form.tsx
6 | AUTH-006 | Drop pinning to studio top | Authoring P2 | Add pinnedDropId to Studio, BFF pinDropToStudio(), workshop pin button, studio page shows pinned drop first | contracts.ts, service.ts, workshop-root-screen.tsx, studio-screen.tsx
7 | AUTH-017 | Alt-text for image preview assets | Authoring P2 | Add altText field to create-drop stepper (type exists in authoring-pipeline.ts), pass through createDrop action | create-drop-stepper.tsx, actions.ts, contracts.ts
8 | AUTH-018 | Captions for video/audio drops | Authoring P2 | Add captionUrl field to Drop, upload in stepper, display in watch/listen modes | contracts.ts, create-drop-stepper.tsx, watch-screen.tsx, drop-listen-mode.tsx
9 | SOC-018 | Hide like counts | Authoring P2 | Add hideLikeCounts boolean to Studio settings, respect in townhall feed social snapshot rendering | contracts.ts, service.ts, settings-account-form.tsx, townhall-feed-screen.tsx
10 | MKT-030 | Brand/sponsored content disclosure | Authoring P2 | Add sponsoredContent boolean to Drop, stepper toggle, display badge on drop cards (like diamond marker) | contracts.ts, create-drop-stepper.tsx, actions.ts, townhall-feed-screen.tsx, globals.css
11 | AID-009 | Set banner image on studio | Studio P3 | Add bannerUrl to Studio, upload field in settings or become-creator, render on studio page | contracts.ts, service.ts, settings-account-form.tsx, studio-screen.tsx
12 | AID-010 | Add external profile links | Studio P3 | Add externalLinks[] to Studio, settings form with add/remove, display on studio page | contracts.ts, service.ts, settings-account-form.tsx, studio-screen.tsx
13 | PRV-005 | Hide drop from specific users | Studio P3 | Add excludedAccountIds to Drop, per-drop settings UI in workshop, enforce in feed/detail queries | contracts.ts, service.ts, workshop-root-screen.tsx
14 | SOC-024 | PRV-003 — Private/locked account | Social P3 | Add isPrivate to Account, follower-request queue, approval UI, enforce in feed visibility | contracts.ts, service.ts, settings-account-form.tsx, studio-screen.tsx